## Task_sheet
Analog_Filter_Board Project Time Sheet
SI No. | Tasks |  | Task Assigned | Strat Date | Due Date | Reviewed | Comments
1 | Serial to Parrallel Register | Design code | Mahesh | 2024-02-03 | 2024-02-09
Test bench code
Simulation Results
Synthesis Reports
Documents
2 | Shift Register | Design code | Mahesh | 2024-02-03 | 2024-02-09
Test bench code
Simulation Results
Synthesis Reports
Documents
3 | FIR Filter Integration | FIR Source code integrate with FIFO before Sending SPI | Suchithra
4 | First in First out memory | Design code | Suchithra | 2024-01-31 | 2024-02-07
Test bench code
Simulation Results
Synthesis Reports
Documents
5 | Serial to Peripheral Integration Slave | Design code | Mahesh | 2024-01-31 | 2024-02-06
Test bench code
Simulation Results
Synthesis Reports
Documents
6 | SPI Avalon Master | Synthesis Reports from qsys tool | Suchithra/Mahesh/Raghunath | 2024-02-12 | 2024-02-15
7 | Control and Timing Block | Design code | Suchithra/Mahesh/Raghunath | 2024-01-26 | 2024-02-16
Test bench code
Simulation Results
Synthesis Reports
Documents
8 | Integration of all blocks | Integration of all modules | Suchithra/Mahesh/Raghunath
Simulation Results
Synthesis Results
Documents
9 | Pinouts | Preparing pinouts documents | Suchithra/Mahesh