## Sheet1
RTL Design Part of Analog Filter Board Project
SI. No. | Topics to be designed
1 | Serial to Parrallel Register
2 | Shift Register
3 | FIR
4 | FIFO
5 | SPI
6 | Cotrol and Timing Block

## Task_sheet
RTL Design Part Deliverables
SI. No. | Tasks | Task Assigned | Start Date | Target Completion Date | Actual Completed Date | Board | Status | Simulations/ Synthesis (SI/SY) | Remarks
1 | Serial to Parrallel Register | Mahesh | 2024-02-03 | 2024-02-09 |  | Max10
2 | Shift Register | Mahesh | 2024-02-03 | 2024-02-09 |  | Max10
3 | FIR Integration | Suchithra |  |  |  | Max10
4 | FIFO | Suchithra | 2024-01-31 | 2024-02-06 |  | Max10
5 | SPI | Mahesh | 2024-01-26 | 2024-01-31 |  | Max10 |  | SI
6 | Control and Timing Block | Mahesh/ Suchithra/Raghunath | 2024-01-26 | 2024-02-16 |  | Max10
7 | State diagram | Mahesh/Raghunath | 2024-02-02 | 2024-02-05
8 | Integration | Mahesh/ Suchithra/Raghunath | 2024-02-09 | 2024-02-16
9 | SPI Avalon Master | Mahesh/ Suchithra/Raghunath
10 | Pinouts | Suchithra/Mahesh